## Slide 1
- Final Presentation -

## Slide 2
Project Risk
  Technical Risk
  - Unclear requirements make implementation and source modification difficult :
  Modify and add requirements to clarify.
  - skill level of java language among individual : assign job by individual skill level
  Resource Risk
  - Lack of human resource to implement new feature : separate developer and tester
  - difficult to select appropriate project management tools : Using external JIRA tools that team members feel familiar.
Product Risk
  Product Quality Risk
  Many unintended errors occurred during the integration of new functions : Simultaneously execute integration test and system test.
Project Risk Management

## Slide 3
Goal : Satisfying Mutation coverage
Goal Coverage
  80% line coverage 80% mutation coverage
Resource
  Planned Effort : 5h (7/23, 1 member, 5 hours)
  Estimated Effort : 10h (7/23, 2 members, each 5hours)
  Actual : 11h (7/23 , 2 members, 6hours + 5hours )
Outputs (ref. appendix.4)
  affected Unit Test Case : GameTest.java - 46 , ItemTest - 3, PlayerTest.java - 4
  Mutation Test Result Report (PIT Summary)
Lessons Learned
  Improvement of Mutation coverage was not directly related to improvement of Unit Test defect detection.  selectively handle the remaining test case bugs provided by the PIT.
  explicit unit test case implementation of the parts to be checked and the degree of stub processing affected the mutation coverage.
  The purpose of the mutation test is to check the fidelity of the test case.
  test case verification of programs that contain a lot of logic to change the value
  test case verification of safety-oriented programs (automotive, aviation-related programs, etc.).
Quality activity – Mutation Test (added)
we did mutation test before implement new feature
Notes: 예상 질문
유닛테스트 작성을 위해 디테일한 스펙을 정리 했는가?

## Slide 4
Goal : Merge the new features into one repository and verify that they are working properly. (Big-bang integration)
Completion criteria
  Test case pass ratio : 100%
Resource
  Planned Effort : 60h
  Estimated Effort : 46.5h
  Actual Effort : 27.5h
Outputs(ref. appendix.5 )
  Test case : 17 (pass rate 100 %)
  Defect list : 7
Lessons Learned
  In the tartan project, the modules are already integrated, should we do the integration test?  it is judged that there are no difference between system test and this integration test
  We could find many issues in the integration with other functions.  For our team, we used integration test more than unit test.
Quality activity – Integration test
Notes: 예상 질문

## Slide 5
Appendix 4. Quality activity – Mutation Test
Before Coverage
After Coverage
Notes: 예상 질문
유닛테스트 작성을 위해 디테일한 스펙을 정리 했는가?

## Slide 6
Appendix 5. Quality activity – Integration test
Test case
Notes: 예상 질문