## Slide 1
- Mid-term Presentation -

## Slide 2
Team members (main role)
  Sungho Chin (Team & Project Lead)
  Jonggu Lee (Code Review Lead)
  Sujung Lyu (Refactoring Lead)
  Jinhyeok Yang (Static Analysis Lead)
  Hyoyeon Hwang (Plan & Test Lead)
Team Goal :
  “Studying and Understanding of SDET Culture and Techniques”, not dancing or singing!!
Team Process :
  Every member should be involved in every quality management process.
  5 hrs for project / day, 1 project meeting / day, 1 mentoring meeting / week
Team introductions

## Slide 3
Project Goal
  “Tracking bugs and defects until our customer(jeff) is satisfied.”
    focus on testability
    => not focus on simple coverage ratio
Quality Goals
  Testability : line coverage : 90%, branch coverage : 80%, mutation coverage : 90%
  Functional correctness : unit test - pass 100%
  Functional suitability for new features : 60%
  Usability (optional) : improve game command and message visibility (can be play the game with the less use ‘help’ command)
Discussion of collected data : team Wiki, JIRA, Sonar, GIthub
Project introductions

## Slide 4
Project Plan
Project Plan
Quality Goals

## Slide 5
Pre-Test (optional) : It is not a formal quality system step
  Ad-Hoc (Experience-based test design technique)
Code review : Team (Technical) Review
Refactoring : Sonar, testability
Unit test : White Box testing (statement testing, branch testing)
Integration test : Scenario testing (gray box)
System test : Scenario testing, Ad-hoc testing, Combination testing, BVA
2nd phase : for new features
  Develop/Unit test
  Code review
  Integration test
  System test
Quality activities

## Slide 6
Goal
  Understanding system of Tartan Adventure.
  checking correspondence between Spec. and Code
  detecting Code defect
Resource
  Participants : All members
  Planned Effort: (6/21 ~ 26) 50h (2h * 5days * 5 members)
  Actual Effort : 36.5h)
Outputs
  number of Defects : 110
Lessons Learned
  Vague requirements made code review hard.
  Code review is one of good way to understanding System.
Quality activities - Code Review

## Slide 7
Goal
  Improving Testability
  Improving Code smells in SonarQube (by 1day debt)
Resource
  Participants : All members
  Planned Effort: (7/9 ~ 13) 50h (2h * 5days * 5 members)
  Actual Effort : 31h
Outputs
  Refactoring status : number of refactoring items (69)
  SonarQube trend:
Lessons Learned
  Refactoring is indispensable for Testability
  Monitoring method for Field Status is needed to know changed status.
  - For this, We discussed for changing private fields to public fields
  - Finally, we added getter & setter methods.
  Method should return about that’s result of procedure.
Quality activities - Refactoring & Re-Work

## Slide 8
Goal
  Quality ‘smell’ of the tartan system
  Review of requirements (at system level)
Resource
  Participants : Sujung Lyu
  Planned Effort: (7/16) 2 h
  Actual Effort : 5 h
Outputs
  TestCase : 26
  Defect : 15
  Map of Game
Lessons Learned
  Understanding the tartan system
  Ambiguous requirements and unexpected gaming behavior
Quality activities - Pre-Test

## Slide 9
Goal : Satisfying code coverage
Completion criteria
  90% statement coverage
  80% branch coverage
Participants : All members
Planned Effort : 45h (7/16~20, 3hours a day)
Actual / estimated Effort : 64h/73h
Outputs
  number of unit-test : 241
  coverage : statement coverage : 88%, branch coverage : 85%
  Defect list : 4 (SDET-47, SDET-48, SDET-51, SDET-54)
Lessons Learned
  Should simple code be included in the Unit test?
   Our team's decision: don’t include
  To effectively write the Unit test, we need a detailed specification.
Quality activity – Unit test
1) methods without conditional statements, getter/setter methods
1)
Notes: 예상 질문
유닛테스트 작성을 위해 디테일한 스펙을 정리 했는가?

## Slide 10
Goal : Verify core sequence consistency (Risk based test)
Completion criteria
  Test case result : 100% pass
Resource
  Participants : All members
  Planned Effort : 45h (7/18~20, 2hours a day) -> 19h 30m
  Actual Effort : 15h 40m
Outputs
  Test case : 11
  pass rate : : 100 %
  Defect list : 1 (SDET-46)
Lessons Learned
  In the tartan project, the modules are already integrated, should we do the integration test?
Quality activity – Integration test
Notes: 예상 질문

## Slide 11
Goals
  Verify requirements from the user's perspective.(2018LGSDETProject.pdf)
  Especially, Use-Cases will be mainly verified.
Resource
  All members
Test Schedule
  Total Man Hours : 50 hours (5days / 5 hours per day / 2 members)
  Periods : 7/19~25
Outputs
  System Test Case
  Test Result
  Defect List (it is managed by JIRA System)
Argument Point
  should we have to implement automation test system?
Quality activity - System test

## Slide 12
System Test (7/19 ~ 7/25)
  two members will do it.
  We will test not only the existing features but also the new features to be developed.
Mutation Test
  one person will do the test
  We will only test the Game class, because it is the core of the game operation.
Implement New Features. (7/23~27)
  3 members
Integration Test for New Features. (7/26~27)
  the number of tester is not determined yet. (New Feature Integration Testing was not decided whether it was a developer or a tester.)
Next Plan

## Slide 13
System Test2 (7/30 ~ 7/31)
  This is the second system test to see if existing defects are resolved successfully and if new functionality is working.
Documentation (8/1 ~ 8/2)
  Document output and prepare for final presentation.
Next Plan (cont.)

## Slide 14
CI : Github + Jenkins (http://40.74.87.221:8080)+ sonaQube
Source repository : github (https://github.com/sunghochin/TartanAdventure)
Quality Tool : SonarQube (http://40.74.87.211:9000/projects)
document configuration : wiki page (https://sdet-bts.atlassian.net/wiki/spaces/SDET/overview)
issue tracker : jira (https://sdet-bts.atlassian.net/secure/RapidBoard.jspa?projectKey=SDET&rapidView=1)
Coverage library : jacoco, pitest
Tools
source commit
Auto trigger build
build
Measure coverage
Static analysis
Coverage integration

## Slide 15
Appendix. Refactoring & Re-Work
Category | num | Graph
adjust access restriction | 36 | 
add return value | 22 | 
method extract | 4 | 
reduce complexity | 2 | 
add new constructor | 2 | 
reduce redundancy | 1 | 
add debug mode | 1 | 
object inject | 1 | 
Refactoring Status

## Slide 16
Appendix. Refactoring & Re-Work
SonarQube Trand

## Slide 17
Appendix. Pre-Test outputs
Defect : 16
Game Map

## Slide 18
Appendix. Quality activity – Unit test
Coverage
Defect list
Notes: 예상 질문
유닛테스트 작성을 위해 디테일한 스펙을 정리 했는가?

## Slide 19
Appendix. Quality activity – Integration test
Test case
Defect list
Notes: 예상 질문