## Report
[Project Title] | [13 empty] | [Company Name / Logo]
Earned Value Analysis Report
Earned Value Management Template
| Prepared By: | [Manager's Name] | [13 empty] | © 2012-2017 Vertex42 LLC
| Date: | [Report Date]
[42]
| For Period: | Week 7
Summary:
[Use this space to write a brief summary or to record specific observations or notes]
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | in Korea | 2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 2018-07-14 | 2018-07-15 | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-28 | 2018-07-29 | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02
1 | Code Review | 50 | 50
2 | Refactoring & Re-Work | 50 |  | 10 | 10 | 10 | 10 | 10
4 | Unit Testing | 55 | [8 empty] | 10 | 10 | 10 | 10 | 5 | [5 empty] | 5 | 5
5 | Integration Testing | 60 | [10 empty] | 10 | 10 | 10 | [5 empty] | 10 | 10 |  |  | 10
6 | Mutation Testing | 5 | [15 empty] | 5
7 | System Testing | 80 | [8 empty] | 5 | 5 |  | 10 | 10 |  |  | 10 | 10 | 10 |  |  |  |  | 10 | 10
8 | New Feature Development | 60 | [15 empty] | 10 | 10 | 10 | 10 | 10 |  |  | 10
9 | Documentation | 60 | [23 empty] | 20 | 20 | 20
0
0
0
0
Insert new rows above this one
| Total Budgeted Cost | 420 | 50 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 15 | 15 | 20 | 30 | 25 | 0 | 0 | 25 | 20 | 20 | 25 | 25 | 0 | 0 | 30 | 30 | 20 | 20
|  | Cumulative Planned Value (PV) | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 115 | 130 | 150 | 180 | 205 | 205 | 205 | 230 | 250 | 270 | 295 | 320 | 320 | 320 | 350 | 380 | 400 | 420
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 36.5 | 40.5 | 44.5 | 49.5 | 54.5 | 57.8 | 57.8 | 58.4 | 80.1 | 110.7 | 134.7 | 134.7 | 154.2 | 154.2 | 189.2 | 200.2 | 210.2 | 233.6 | 253.6 | 265.4 | 280.4 | 295.4 | 325.4 | 346.4 | 346.4 | 346.4
|  | Cumulative Earned Value (EV) | 50 | 53 | 57 | 62 | 67 | 69.3 | 69.3 | 69.9 | 90.6 | 115.2 | 144.2 | 144.2 | 166.7 | 166.7 | 181.7 | 191.7 | 206.7 | 239.7 | 264.7 | 275.7 | 285.7 | 295.7 | 331.7 | 353.2 | 353.2 | 353.2
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 13.5 | 12.5 | 12.5 | 12.5 | 12.5 | 11.5 | 11.5 | 11.5 | 10.5 | 4.5 | 9.5 | 9.5 | 12.5 | 12.5 | -7.5 | -8.5 | -3.5 | 6.1 | 11.1 | 10.3 | 5.3 | 0.3 | 6.3 | 6.8 | 6.8 | 6.8
|  | Schedule Variance (SV = EV - PV) | 0 | -7 | -13 | -18 | -23 | -30.7 | -30.7 | -30.1 | -24.4 | -14.8 | -5.8 | -35.8 | -38.3 | -38.3 | -23.3 | -38.3 | -43.3 | -30.3 | -30.3 | -44.3 | -34.3 | -24.3 | -18.3 | -26.8 | -46.8 | -66.8
|  | Cost Performance Index (CPI = EV/AC) | 1.3699 | 1.3086 | 1.2809 | 1.2525 | 1.2294 | 1.199 | 1.199 | 1.1969 | 1.1311 | 1.0407 | 1.0705 | 1.0705 | 1.0811 | 1.0811 | 0.96036 | 0.95754 | 0.98335 | 1.0261 | 1.0438 | 1.0388 | 1.0189 | 1.001 | 1.0194 | 1.0196 | 1.0196 | 1.0196
|  | Schedule Performance Index (SPI = EV/PV) | 1 | 0.88333 | 0.81429 | 0.775 | 0.74444 | 0.693 | 0.693 | 0.699 | 0.78783 | 0.88615 | 0.96133 | 0.80111 | 0.81317 | 0.81317 | 0.88634 | 0.83348 | 0.8268 | 0.88778 | 0.89729 | 0.86156 | 0.89281 | 0.92406 | 0.94771 | 0.92947 | 0.883 | 0.84095
|  | Estimated Cost at Completion (EAC) | 306.6 | 320.9434 | 327.8947 | 335.3226 | 341.6418 | 350.303 | 350.303 | 350.9013 | 371.3245 | 403.5937 | 392.3301 | 392.3301 | 388.5063 | 388.5063 | 437.3363 | 438.6228 | 427.1118 | 409.3116 | 402.3876 | 404.309 | 412.2086 | 419.5739 | 412.0229 | 411.9139 | 411.9139 | 411.9139
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP). | [15 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [15 empty] | © 2012-2017 Vertex42 LLC
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | in Korea | 2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 2018-07-14 | 2018-07-15 | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-28 | 2018-07-29 | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02
1 | Code Review | 50 | 50
2 | Refactoring & Re-Work | 50 |  | 3 | 4 | 5 | 5 | 2.3 |  | 0.6 | 3.7 | 7.6 | 2
4 | Unit Testing | 55 | [8 empty] | 15 | 15 | 27 | [11 empty] | 8
5 | Integration Testing | 60 | [12 empty] | 19.5 | [9 empty] | 15 | 3
6 | Mutation Testing | 5 | [15 empty] | 5 | 5
7 | System Testing | 80 | [8 empty] | 2 | 2 | [7 empty] | 13 |  | 6.5 |  |  | 3 | 0.5
8 | New Feature Development | 60 | [15 empty] | 5 | 10 | 20 | 25 | 4.5 | 10 | 10 | 10
9 | Documentation | 60 | [12 empty] | 3 |  | 15 | [8 empty] | 18
- | - | 0
- | - | 0
- | - | 0
- | - | 0
Insert new rows above this one
|  | Cumulative EV | 50 | 3 | 4 | 5 | 5 | 2.3 | 0 | 0.6 | 20.7 | 24.6 | 29 | 0 | 22.5 | 0 | 15 | 10 | 15 | 33 | 25 | 11 | 10 | 10 | 36 | 21.5 | 0 | 0
|  |  | 50 | 53 | 57 | 62 | 67 | 69.3 | 69.3 | 69.9 | 90.6 | 115.2 | 144.2 | 144.2 | 166.7 | 166.7 | 181.7 | 191.7 | 206.7 | 239.7 | 264.7 | 275.7 | 285.7 | 295.7 | 331.7 | 353.2 | 353.2 | 353.2
|  | Cumulative EV | 2500 | 150 | 200 | 250 | 250 | 115 | 0 | 30 | 1170 | 1365 | 1585 | 0 | 1350 | 0 | 900 | 325 | 625 | 2240 | 1500 | 790 | 600 | 600 | 2180 | 1300 | 0 | 0

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period. | [15 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [15 empty] | © 2012-2017 Vertex42 LLC
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | in Korea | 2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 2018-07-14 | 2018-07-15 | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-28 | 2018-07-29 | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02
1 | Code Review |  | 36.5
2 | Refactoring & Re-Work |  |  | 4 | 4 | 5 | 5 | 3 |  |  | 4.7 | 7.6 | 2
4 | Unit Testing | [6 empty] | 0.3 |  | 0.6 | 15 | 20 | 22 | [11 empty] | 6
5 | Integration Testing | [13 empty] | 15.5 | [10 empty] | 4
6 | Mutation Testing | [15 empty] | 5 | 6 | [6 empty] | 12
7 | System Testing | [9 empty] | 2 | 3 | [7 empty] | 10.4 |  | 6.3 |  |  |  | 0.5
8 | New Feature Development | [16 empty] | 5 | 10 | 13 | 20 | 5.5 | 15 | 15 | 12
9 | Documentation | [13 empty] | 4 |  | 30 | [8 empty] | 16.5
- | -
- | -
- | -
- | -
Insert new rows above this one
|  | Total Actual Cost | 36.5 | 4 | 4 | 5 | 5 | 3.3 | 0 | 0.6 | 21.7 | 30.6 | 24 | 0 | 19.5 | 0 | 35 | 11 | 10 | 23.4 | 20 | 11.8 | 15 | 15 | 30 | 21 | 0 | 0
|  | Cumulative Actual Cost (AC) | 36.5 | 40.5 | 44.5 | 49.5 | 54.5 | 57.8 | 57.8 | 58.4 | 80.1 | 110.7 | 134.7 | 134.7 | 154.2 | 154.2 | 189.2 | 200.2 | 210.2 | 233.6 | 253.6 | 265.4 | 280.4 | 295.4 | 325.4 | 346.4 | 346.4 | 346.4

## ©
Earned Value Management (EVM) Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/critical-path-method.html
© 2012-2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.